========

Tutorial

========

The RPM tutorial is designed to give you a quick overview of the system's

operation.  Lesson 1 shows you how to develop your projects database.

Lesson 2 shows you how RPM's facilities can be used to analyze your

project, resolve scheduling and resource conflicts and print reports.

Lesson 1 starts with a partial projects database involving just a

few resources and projects.  You will complete this database in Lesson

1 and then build on the results in Lesson 2.

Warning: While you should feel free to experiment using the

"Tutorial" projects database, do not develop any of your "live"

projects in this database.  If and when you re-install later versions

of RPM, this database will be overwritten and your work will be

lost.

Lesson 1 -- Developing the Projects Database

============================================

A projects database is the collection of files that describe your

project environment.  It consists of the projects and resources

files, and the calendar file.  This lesson will teach you how to

develop these files.

Setting up the Calendar

-----------------------

The first step is to select and develop your calendar.  Simply

stated, the calendar is a list of holidays or non-working days.  RPM

comes supplied with two calendar files which you may modify or use

as is.  They are USA.CAL and CANADA.CAL and each contains the usual

holidays for each country extending for some time into the future.

In general, you will only need to set up your calendar once.

1   Select System from the main menu.

2   Cursor to the Calendar File Name field and press F1.

3   For the purposes of this lesson, select the USA calendar (the

default).  When you develop your own projects, make sure that the

appropriate calendar is selected.

4   Feel free to explore this screen and experiment with various

options.  The meaning of all these options may not be immediately

clear.  Remember, help is available by pressing F10.  Return to the

main menu (press Escape) when you are ready.

That is all there is to calendar setup unless your company has

non-standard working days.  To check the holidays in the calendar you

have selected and, if necessary, to change them, perform the

following steps:

1   Select Calendar from the main menu.

2   Verify that the holidays defined are correct.  The standard calendar

sets Saturdays and Sundays as non-working.  If you wish to change any

day or date to non-working or vise versa, simply cursor to it and

press F1.

3   Use the page up and down keys to move through the years.

4   When finished, press Escape to return to the main menu.

This calendar will be saved when you exit the system and will be

automatically re-loaded when you re-invoke RPM.  The RPM "readme"

file contains a list of holidays for the USA and Canada that are set

in the RPM supplied calendar files USA.CAL and CANADA.CAL.

Setting up Resources

--------------------

The underlying data defining a company consists of the calendar and

the company's resources.  You will now see how to define new

resources and how to create "summarizing" resources.

First, load the sample project and resource file called Tutorial.

1   Select System from the main menu.

2   Cursor to the Projects File Name field.  If this field already

specifies the projects file called TUTORIAL (the default), you may

skip the next step.  Otherwise, press F1.

3   Select TUTORIAL.

A message will appear saying that the new project file has been

loaded.

4    Press Escape twice to return to the main menu.

The sample projects database TUTORIAL already has a number of

resources defined.  First, you will define a summary resource and

then a new employee.

5   Select Resources.

6   Press F1.  This will bring up a list of already defined resource and

some additional options.  Select New.

7   Type the new resource name PM (for Project Management) and press

Enter.

8   Enter the following data for the project management resource:

Name:      Project Management

Avail:     0

Rate:      0

You have now defined a new resource called "project management."

Zero hours have been set as the availability because next you will

define an employee whose availability will contribute to that of

project management.

We are defining availabilities in hours per day and therefore the

rate is expressed in dollars per hour.  Rates and availabilities may

use any units -- but once a unit is selected, it must be uniformly

applied.

9   Now press the Home key.  This will bring you back to the Resource

Name field.

10  Once again, press F1, select New and define a resource with the

following data: Name: BSmi; Description: Bill Smith; Rate: 0; and

Avail: 7.5.

Resources can be associated one with another.  If two resources are

associated with each other, one is said to summarize the other, and

the other to contribute to the first.  Resources that summarize other

resources are also called "meta-resources" (i.e.: resources of

resources).  We wish to make Bill Smith a Project Manager and a

Professional Engineer Level 2.  The first association will allow us

to track the utilization of Project Managers.  The second association

will establish the rate that Bill Smith will have.  In this case,

Bill Smith will contribute to both these resources.

11  To make Bill Smith contribute to Project Management and to

Professional Engineer Level 2, cursor the the Edit Summarizing

Resources field and press F1.  The list is initially empty.

12  Press the Ins key to get a list of possible resources that Bill

Smith could contribute to.  Cursor to each of Project Managers and

Professional Engineer Level 2 and press the space bar.  Then press

Escape.

Now Bill Smith contributes to these two resources.  Additional

employees could be defined in a similar way.  The association with

Project Managers will allow us to track Project Manager availability

and utilization.  Bill Smith's availability and utilization will be

added to that of Project Managers.  This is also true of Professional

Engineer Level 2, but this association was made primarily to assign

a rate to Bill Smith.  Since Bill Smith has a zero rate, he will

inherit the rate of Professional Engineer Level 2 which is $95/unit.

13  Use the Escape key to return to the main menu.

Like calendars, the definitions of resource need only be done once

(or when your staffing levels or resource availabilities change).

Also like calendars, the definitions of resources will be saved

automatically when you exit the system.  Unlike calendars, resources

are associated with, and saved with, a projects database.

Defining Projects

-----------------

With the underlying calendar and resources in place, you can now

begin the real work of defining and managing projects.

1   Select Spreadsheet from the main menu.

2   Press F1, and then choose Select (i.e.: press F1 twice).

3   Select the project called Lesson.

This is the basic project planning spreadsheet.  As you can see, a

project consists of some basic data located at the top of the screen

(such as the code, the name, the project manager's name etc.) and a

spreadsheet that occupies the remainder of the screen.  The

spreadsheet has the project's phases as rows and the project's

resources as columns.  The spreadsheet cells contain the resource

units (in this case, hours) that each phase uses.

Around the outside of the spreadsheet are phase and resource totals

and percentages of the grand total (which appears at the lower left

of the screen).  These values are kept up-to-date at all times by the

system.

Defining a project consists of supplying the basic data that appears

at the top of the screen and then adding phases and resources to the

spreadsheet.

This project is complete except for a number of changes and

additions you are going to make.  You will:

* add one additional phase called Phase 6;

* add the resource "project management";

* assign project management hours to the new phase and resource;

* and extend the duration of the total project by 10 days.

Before doing these tasks, lets take a quick look at the Gantt

screen.

4   Press F2.

You are now looking at the Gantt screen, with the Lesson project at

the top of the screen.  The Gantt screen is the best place to

manipulate date information associayed with a project.  The

Spreadsheet screen is the best (and only) place to enter and

manipulate the hours associated with a project.

5   Press F2 again to return to the Spreadsheet.

You may flip between the Gantt and Spreadsheet anytime by pressing

F2.

Finally, before going on to add the new resources and phases to the

Lesson project, lets take a quick look at the other projects in the

database.  There are two others.

6   Press Ctrl-Page Down to "page through the projects database.  This

will take you to Project 1.  Press Ctrl-Page Down two more times to

return to the Lesson project.  (Alternatively, press Ctrl-Page up

once.)

Adding Phases to a Project

--------------------------

1   Use the End key to move the cursor to the last cell on the screen.

This is the cell immediately below the last phase defined on the

screen.

2   Enter the code Phase 6 and press enter.

3   Enter the following phase information:

Name:                      Post Construction

Level of Effort Phase:     N

Start Date:                14 April 90

Duration:                  90 days

Notice that Saturday, 14 April 1990 was advanced to a working day.

Also, when you entered the duration, the finish date changed

automatically.  You could have entered the finish date if you

preferred, in which case the duration would have changed to 90 days.

4   Press Escape.

You have now added a new phase to this project.  Notice that the

project finish date at the top right of the screen has been updated

to reflect the end date of the new phase and that a new row of cells

has been added to the spreadsheet.

Adding New Resources to a Project

---------------------------------

1   Use the arrow keys to move the cursor to the cell just to the right

of the last resource (in this case, "KPhe") and press F1.

A small menu will appear allowing you to select Resources.

2   Select Resources and then select Project Management.

You have now added a new resource to this project.  Notice that a new

column of cells has been added to the sheet.

Adding Hours to a Project

-------------------------

3   Use the arrow keys to position the cursor at the top of the new

column.  You can add new hours to each cell by typing the value

desired and pressing enter.

4   Add the following values vertically in this new column for the first

five phases:

120; 200; 350; 75; 700, 50.

5   Now do the same for the new Phase 6 row and add horizontally the

following values:

50; 75; 60; 40; 220; 50.

Changing the Length of a Project

--------------------------------

1   Use the arrow keys to move the cursor to the project start date

which is located at the top right of the screen and press F1.

This screen allows you to manipulate the project's dates and its

duration.

2   Cursor to the duration, change the value from 283 to 293 and press

Escape.

Notice that the project finish date has changed.  As well the start

and end dates of each phase have been adjusted to reflect the longer

project.

Saving Your Data and Returning to DOS

-------------------------------------

1   Press Escape twice and you will be returned to the main menu and be

asked if you would like to quit.  Answer Y for Yes and you will be

returned to DOS.  The changes you have made will be saved

automatically.

The project file Tutorial will be loaded automatically the next time

you invoke RPM.

If you wish to repeat this lesson, answer N for No and then select

the System option off the main menu.  Use F1 on the Project File

field and change the name of the project file to some other value.

Now when you exit the system, RPM will save the changes you have

made under this new file name.

Alternatively, you could select File from the main menu option and

select Drop Reservation from the menu that will appear.  Dropping the

reservation will make the Lesson database "read-only." This feature

is very similar to that used by Lotus 1-2-3 (versions 2.2 and

greater) to control access to worksheets in a network environment.

If you do not have the reservation on a projects database, it will

not be saved at the end of a session.

Other Things to Try

-------------------

Make sure that you are in the Spreadsheet screen and are looking at

the Lesson project.

Cursor to the field called "Notes" and press F1.  You will see a

sample notes file that you can edit.  Press F7 to save any changes

(or F1 to cancel and changes) and return to the Spreadsheet screen.

Notes can be entered for both projects and phases.

Cursor to the field next to Notes called "Active" and press F1.  This

toggles the project to Pending.  Pending projects are ignored in

utilization calculations.  Press F1 to toggle the project back to

Active.  Setting a project to Pending is approximately the same as

setting the "% Likelihood" value to zero.

Cursor to the field called "Hours", press F1, and select Dollars.

The display will now be in dollars rather than hours.  Press F1 again

and select Hours to set the display back to hours.

Cursor to the field called "Progress Date" and enter a date.  Enter

the same date as the project start date.  Now cursor to the field

called "Allocated View" and press F1.  You will be presented with a

list of different possible views of the project.  Feel free to

explore the various views.

Finally, cursor to any cell in the Spreadsheet and press F1 twice

(you must have entered a Progress Date).  You will now see the pop-up

progress window.  You can enter progress data for each cell using

this window.

Summary

-------

In this lesson, you have learned how to:

select and modify the calendar to reflect the holidays appropriate

for your company;

define new resources and associate them one with with another;

add phases, resources, and hours to a project;

modify the dates associated with phases and projects;

move between projects and to and from the Gantt screen;

and save your data.

If you did the "Other Things to Try", you also know how to enter

notes, change units and views, and enter progress data.

===============

End of Lesson 1

===============

=============================================

Lesson 2 -- Analyzing Resources and Reporting

=============================================

Before beginning this tutorial, invoke RPM as described in Installation.

In the last lesson, you learned how to develop the projects database

These data, combined with the analysis tools provided by RPM, allow

you to anticipate potential resource and scheduling problems in your

company and implement solutions for them.

Load the Company Model

----------------------

As before, you must ensure the appropriate projects database is loaded.

If you are continuing from Lesson 1, the correct model will be loaded

automatically.  Otherwise, load the project file called Tutorial

as follows:

1   Select System from the main menu.

2   Cursor to the Project File Name field and press F1.

3   Select Tutorial.

A message will appear saying that the new project

file has been loaded.

4   Press Escape twice to return to the main menu.

A resource problem can arise for a number of different reasons but

stated simply, a problem exists if -- at any time -- resource

requirements exceed resource availabilities.  In this circumstance,

the current schedule is not a possible one.  To solve the problem,

resources can be acquired, jobs rescheduled, work scope reduced etc..

To see if a problem exists, select Gantt/Utilization from the

main menu.  The following screen will appear:

This screen simultaneously displays two utilization curves for the

aggregate resource All: the total resource utilization curve

for all projects and the contribution of the project indicated by

the current cursor location -- in this case, project Lesson.

In general, the aggregate resource utilization curve is not particularly

useful.  More important is the utilization curves for specific resources.

Examining Resource Utilization Curves

-------------------------------------

5   Use the function keys F3/F4 (shrink/grow) and F5/F6 (page

left/right) to manipulate the display until you can see the

beginning of the Gantt line for the project Lesson.  (You will need

to press F3 about twice.)

6   Press the End key to move the cursor to the resource field at the

bottom of the screen.

7   Press F1; select Resources; and then select Arch for architects.  The

screen will now appear as follows:

As you can see, there is a problem with architects.  According to the

display, architects are over-utilized in the month of July.

8   To determine which project(s) contribute to this problem, cursor up

the screen.

As the cursor moves to each new project, the highlighted project

changes.  When you get to project Lesson, you will see that this

project contributes greatly to the over-utilization of architects in

the month of July.

9   Press F1 and select Explode to cause RPM to display the phases for

the project.  Your screen will now appear similar to Fig.  2-12.

10  You can see that Phase 2 looks like it is part of the problem.

(Actually, it is the overlap of phases 1 and 2 which creates the

problem.) There are a number of ways that this problem could be

addressed:

*   You could increase the duration of the first phase and thus decrease

its daily utilization of architects.  This can be accomplished either

by cursoring to the phase and editing it by pressing F2 or, more

simply, by pressing the + key.  Pressing the plus key increases the

duration of Phase 2, and thus decreases the daily utilization of

architects.

*   You could move Phase 2 into the future.  This could be accomplished

by either editing the phase as described above or by pressing the >>

key while the cursor is on the second phase.

*   You could use RPM's Resource Leveling feature to level the resource

utilizations within a project.

We will use the first solution.

11  Cursor to Phase 1, press the + key a number of times.  Each time you

press this key, the duration of the phase will be increased and you

will observe a corresponding decrease in the daily utilization of

architects during the period.  The amount the duration is increased

will depend on the current scale.  You can see the duration displayed

on the status line at the bottom of the screen.

Obviously, this approach may not always be appropriate.  It may

result in an unacceptable schedule and some other solution may be

required.  For our purposes, we will assume that the problem is

solved.

Printing Reports

----------------

Now that you have analyzed your project data and have arrived at an

acceptable schedule, it is time to print reports.

1   Press Escape to return to the main menu.

2   Select Reports and then Run Reports.

We wish to execute a Gantt report and a resource utilization report

for architects.

3   Press F1 and select Tabular Reports and then select the report

definition GANTT.

4   Cursor to the field called Gantt/RU Start and enter 17Jul89.  This

sets the dates that will appear in the Gantt portion of the report

to appropriate values.

5   Review the Printer Type and Setup values.  The default RPM printer

type and settings are appropriate for most printers for compressed

printing.

6   Cursor to the field called EXECUTE and press F1.  The Gantt report

will be sent to your printer.

7   Cursor to the report type field (press Home), press F1 and select

Resource Utilization Report.  You will be prompted to set special

options for this report.  For now, do not change these values.  Simply

press escape.

8   Cursor to the projects field, press F1, and select the project

Lesson.  This will indicate to RPM that the Resource Utilization

report should highlight the contribution to resource utilization

curves of the project Lesson.

9   Cursor to the resources field, press F1, select Resources and then

Arch.  This will select architects as the resource against which you

will run your resource utilization report.

10  Cursor to the field called EXECUTE REPORT and press F1.  The resource

utilization report will be sent to your printer.

11  Press Escape twice and answer Yes (Y) to return to DOS.  Your changes

will be saved automatically.

Other Things to Try

-------------------

Return to the Gantt screen.

Place the cursor on any project, press F1, and select Set Display

Options.  If you have an EGA or VGA board in your PC, select the

appropriate Display type.  Then increase the Number of Resources to 2

(3 or 4 if your display is EGA or VGA).  Press Escape.  Your display

will now show more than one resource utilization curve.  By selecting

different resources to display, you can analyze utilizations across

projects and across resources.

Once again, press F1, and select Set Display Options.  Set Highlight

Phases to yes.  Press Escape.  Now press F1 again and select Explode

All Projects.  Now, as you cursor through the projects and phases,

each project and each phase will be highlighted.  This allows you to

see the impact of each project and phase on the total utilization.

Summary

In this lesson, you have been introduced to the techniques required

to analyze and correct resource utilization problems.  Also, you have

seen how reports can be obtained.  RPM also allows you to develop

your own reports.  See Defining Reports in the Reference Section for

details on this process.

===============

End of Tutorial

===============